Before the

FEDERAL COMMUNICATIONS COMMISSION

Washington, D.C. 20554

In the Matter of					)

)

Request for Waiver of				)

Special Construction Service Delivery Deadline	)

CENIC-CORPORATION FOR EDUCATION	)

NETWORK INITIATIVES IN CALIFORNIA	)

Schools and Libraries Universal Service		)	CC Docket Nos. 02-6, 13-184

Support Mechanism				)

REQUEST FOR A WAIVER OF THE COMMISSION’S RULES BY CENIC-CORPORATION FOR EDUCATION NETWORK INITIATIVES IN CALIFORNIA FOR THE SERVICE DELIVERY DEADLINE OF A FUNDING YEAR 2016 LIT FIBER SPECIAL CONSTRUCTION FUNDING REQUEST

Date	August 24, 2018

Appellant/Organization Name	CENIC-CORPORATION FOR EDUCATION NETWORK INITIATIVES IN CALIFORNIA

Funding Year				2016

Entity Number				225495

FCC Form 471	Number		161059583

Funding Request Number		1699138777

Service Delivery Deadline		6/30/2018

Invoice Deadline			10/29/2018

In accordance with sections 54.719 and 1.3 of the Commission's rules, CENIC-CORPORATION FOR EDUCATION NETWORK INITIATIVES IN CALIFORNIA (“CENIC” or “Applicant”) requests the Federal Communications Commission’s (“FCC” or “Commission”) to grant a Waiver of the Commission’s rules for the service delivery deadline for special construction for lit fiber services for the betterment of the public’s interest and/or due to extraordinary circumstances.

BACKGROUND

As the statewide consortium applicant for California, CENIC is arguably one of the largest applicants in the E-rate program in terms of number of consortium members, number of students and library patrons served, number of annual funding requests, and the scope of broadband services procured for eligible schools and libraries. In its role as consortium lead, CENIC applies for E-rate funding on behalf of the statewide K-12 network, middle and last mile broadband connections for public libraries, and for recipients of the State of California’s Broadband Infrastructure Improvement Grant (BIIG) as referenced in the Second E-rate Modernization Order and USAC’s website for eligible state-matched special construction projects.

The funding request under review in this Request for Waiver is for special construction of a lit fiber service for a grantee of California’s BIIG program: Klamath-Trinity Joint Unified School District. The school locations served by this District are located in very rural forested areas of inland Humboldt County, the majority of which are entirely located within the Hoopa Valley Tribal Reservation. Despite having started the project in August 2016, 15 months prior to USAC’s issuance of the Funding Commitment Decision Letter, the service provider, Hunter Communications, experienced numerous delays and setbacks and will not be able to deliver services until after the current extended service delivery deadline of June 30, 2018. These delays and setbacks were due to the following circumstances:

- Protracted pole permitting processes with the power company and Incumbent Local Exchange Carrier (“ILEC”) as outlined in Exhibit B Pole Permitting Process and Timeline;

- Environmental and archeological studies due to the locations where construction will occur (e.g., tribal lands and protected redwood forest and riparian habitats);

- Winter weather conditions; and

- Wildfires.

It is anticipated that the service will be delivered by the end of the calendar year 2018. However, it should be noted that construction may be halted and further delayed if unanticipated and significant cultural or environmental circumstances are discovered during the construction process.

REQUEST FOR WAIVER

In reviewing the rules establishing the one-time allowable extension of special construction funding requests, it is significant to note that all of the language in the Second E-rate Modernization Order pertains to the lighting of dark fiber or self-provisioned networks, and not for lit fiber.  For example, the first reference for the single one-time allowable extension is in Paragraph 37:

To prevent applicants from using E-rate discounts to acquire unneeded capacity or

warehouse dark fiber for future use, we maintain the safeguards that the Commission adopted in the Schools and Libraries Sixth Report and Order, and extend those it adopted in the Healthcare Connect Order to E-rate. First, to prevent warehousing of excess fiber capacity, applicants cannot receive E-rate funding for recurring costs associated with dark fiber until it is lit, and applicants may only receive funding for special construction charges for dark fiber if it is lit within the same funding year. (emphasis added)

This is re-iterated in Paragraph 38:

Because special construction charges for leased dark fiber are now eligible for category one support, applicants seeking support for special construction for dark fiber may avail themselves of this limited exception for early construction. In addition, as in the Healthcare Connect Order, we will also allow applicants to receive up to a one-year extension to light fiber if they demonstrate that construction was unavoidably delayed due to weather or other reasons. (emphasis added)

And then again in Paragraph 49 related to self-provisioned networks:

Second, as with applicants that seek E-rate support for dark fiber, to ensure that we are

paying for necessary services, applicants may only receive funding for self-construction if the facilities are built and used within the same funding year. Pursuant to the prohibition against reselling service purchased with E-rate discounts,105 applicants may only receive E-rate support for services that they use. In Section II.B.1, we codified a limited exception to allow funding for special construction charges for projects started up to six months in advance of the funding year, provided the following conditions are met: (1) the construction begins only after selection of the service provider pursuant to a posted FCC Form 470 (or any successor form); (2) a category one recurring service must depend on the installation of the infrastructure; and (3) the actual service start date is after the start of the funding year (July 1).  This exception applies to self-construction. As we do with dark fiber, we will also allow applicants to receive up to a one-year extension of the service start date if they demonstrate that construction was unavoidably

delayed due to weather or other reasons. (emphasis added)

In reviewing the context of and the actual statements made in the Second E-rate Modernization Order, there is no reference tying the newly-established rule of service delivery and the single allowable one-year extension to special construction of lit fiber services. We therefore ask the FCC to reconsider if this rule was intended by the Commission to be applied to lit fiber special construction funding requests.

Should the Commission agree with our perspective that the lit fiber special construction funding request should not be held to the same rules as dark fiber and self-provisioned networks, we ask that the Commission allow for the applicant to receive a service delivery deadline extension on Funding Request Number 1699138777 to September 30, 2019 and the associated invoice deadline of January 28, 2020. We also ask that the applicant be able to request additional extension(s) should they be necessary due to unforeseen circumstances such as the discovery of significant cultural or environmental circumstances.

WAIVER IN THE PUBLIC INTEREST

In the event the Commission does not agree with our assessment that the provisions of the Second E-rate Modernization Order should not be applied against lit fiber special construction funding requests, we ask that the Commission waive its rules in the public interest. The schools receiving lit fiber service under this funding request are severely underserved. They are located in some of the most remote locations in the State, including those on Tribal lands, and serve a high-poverty student population. The diligence shown by the service provider throughout the two-year process to bring service to the schools under extremely difficult circumstances is, we believe, further justification for the waiver. We hope that the FCC will view the challenges described in this request in the same light as it did for the Waiver Request filed by the Utah Education and Telehealth Network (UETN) and provide similar relief as it did to UETN.

ALTERNATIVELY, WAIVER FOR EXTRAORDINARY CIRCUMSTANCES

We also ask the Commission to consider the evidence on record in this and UETN’s waiver request that a single one-time request for extension of the service delivery deadline for special construction is prohibitive in many instances and should perhaps be revisited. There are often multiple extenuating and compounding circumstances that may lead to a delay in a project outside of a late-issued funding commitment decision letter or “weather or other reasons.” As illustrated in this request, weather was only one component in the delay. The other factors - delays and difficulty in securing pole permits, regional natural disasters (e.g. wildfires), and compliance with cultural and environmental federal and state laws - all acted in confluence making the project incredibly challenging and required the absolute tenacity of multiple parties to bring to a positive outcome.  We are concerned that the strict interpretation of the single one-time extension will be a deterrent to both applicants and service providers in bringing high speed broadband over lit fiber to rural and impoverished communities.

SUMMARY

CENIC asks that the FCC waive its service delivery deadline rules for lit fiber special construction funding request number 1699138777 taking into consideration the statements and other information set forth in this request. We ask that the service delivery deadline be extended to September 30, 2019 and invoice deadline to January 28, 2020 subject to further request for extension, should it be warranted. We believe that this is in the public’s interest of providing high-speed scalable broadband services to rural and impoverished schools.

Finally, there is no evidence in the record that CENIC engaged in activity intended to defraud or abuse the E-rate program.  Denying its request for service delivery extension would create undue hardship and prevent it from receiving E-rate funding for eligible services already paid to the service provider.  Accordingly, good cause exists to grant CENIC a Waiver of the Commission’s rules.

We appreciate your consideration of our request.  Any additional questions, concerns or request for additional documentation related to this appeal should be directed to:

Cathy Benham

CSM Consulting, Inc.

cbenham@csmcentral.com

909-944-7798

Respectfully submitted,

/s/

Cathy Benham

Director of Consulting Services

3130-C Inland Empire Blvd.

Ontario, CA 91764

In Funding Year 2018, CENIC had 1,225 consortium members which represent over 10,000 schools and 700 libraries for whom CENIC filed 223 funding requests for over 1,000 broadband connections.

https://www.k12hsn.org/special-projects/biig2

FCC 14-189 SECOND REPORT AND ORDER AND ORDER ON RECONSIDERATION, Para. 55

https://www.usac.org/sl/applicants/beforeyoubegin/state-matching-provision.aspx#CA

https://en.wikipedia.org/wiki/Humboldt_County,_California

https://www.hoopa-nsn.gov/the-tribal-government; http://www.hoopaforestry.com/

See Exhibit A Letter from Hunter Communications

http://www.dot.ca.gov/ser/vol2/vol2.htm

https://ecfsapi.fcc.gov/file/102210564507114/UETN%20Daggett%20Waiver%20Petition.pdf

DA 18-473 Utah Education and Telehealth Network Waiver Order