Before the

Federal Communications Commission

Washington, DC 20554

In the Matter of:

)

Request for Review of a decision		)

by the Schools and Libraries Division	)	Administrator Correspondence Dated

for Virginia Beach City Public Schools	)	August 7, 2018

Virginia Beach, VA				)

)

)

Schools and Libraries Universal Service	) 	CC Docket No. 02-6

Support Mechanism				)

Request for Review

In accordance with Sections 54.719 through 54.721 of the Commission’s Rules, Virginia Beach City Public Schools (Virginia Beach) appeals this decision of the Schools and Libraries Division of the Universal Service Administrative Company (Administrator).   The Administrator improperly denied a Service Delivery Extension Request and denied the subsequent Virginia Beach appeal.

In accordance with longstanding precedent and clear procedures, Virginia Beach asks the Commission to overturn this decision and instruct the Administrator to extend the service delivery and invoice deadlines for this funding commitment.

This appeal comes timely submitted within 60 days of the Administrator decision.

Requestor: Virginia Beach City Public Schools

Billed Entity Number: 126526

FCC Registration Number 0011821147

Funding Request Number:1699094476

Form 471 Numbers: 161039047

Background

For Fund Year 2016 Virginia Beach determined a replacement of its core switching network was necessary and contracted with ABS Technology for purchase and installation of core equipment and cabling for the school division. Virginia Beach submitted and certified E-Rate Form 471 number 161039047 on May 24, 2016, within the Fund Year 2016 filing window. This application was 269 pages and 107 individual line items. It included core replacements at four sites including routers, UPS’s, connectors, cabling, installation and maintenance. The total cost for this application was $1,635,523.92 with an E-Rate funding request of $981,314.35.

This application was subjected to a protracted Administrator review and ultimately funded on January 27, 2017, giving Virginia Beach just seven months to complete the entire project by the September 30, 2017 equipment installation deadline. It should be noted here that in Fund Year 2016 Virginia Beach had 29 E-Rate applications representing approximately $6 million in equipment and services. All applications were filed within the 2016 filing window and all without the assistance of an E-Rate consultant.

Once E-Rate funding had been approved, several post-commitment actions were required to extend the ABS contract reported on the Form 471, adjust service start dates and, for the FRN here under appeal, to extend the service delivery date beyond September 30, 2017. The stated reason for the service delivery extension was for reasons beyond the service provider’s control. Specifically: “Problem with the building electrical system have delayed the installation of the UPSs.” This Form 500, Number 71673, was pending at USAC for nine months and finally denied on June 23, 2018. Virginia Beach appealed the decision to the Administrator on July 19, 2018 and was denied on August 7, 2018. The Virginia Beach appeal to the Administrator appeal was perfunctory because of assurance by the Administrator in January 2018 emails that the Form 500s filed by Virginia Beach and denied were “…done in error.”

Relevant documents attached: Form 500 Number 71673 and Administrator denial, Attachment A; Virginia Beach USAC Appeal and Administrator Denial, Attachment B; Virginia Beach/Virginia DOE/Administrator correspondence, Attachment C.

Discussion

The Administrator erred when denying this service delivery extension request both with the Form 500 denial and on appeal. Work on this extensive project was delayed by a protracted application review with a funding commitment issued almost seven months after start of the fund year, compounded by delays with processing Form 500’s to extend the Form 471 contract expiration date.

Once installation finally began, Virginia Beach discovered an electrical issue at one of the installation sites. To resolve the issue, an electrical survey was required to determine if wiring was adequate and the on-site generator could support the additional load. These delays were outside the control of the service provider and could not have been reasonably anticipated by Virginia Beach when submitting the Form 471.

The Commission has held on that service delivery for one-time charges could be extended for numerous reasons. First, if the Funding Commitment Decision Letter is issued after March 1 of the relevant fund year, an automatic one-year extension is granted. In this case, the Funding Commitment Decision Letter was issued on January 27, 2017 a mere 30 days before an automatic one-year extension would have been granted. Second, delays with processing Forms 500 to extend the contract expiration date delayed implementation and finally, issues involving the electrical infrastructure at a the installation site, outside the control of the service provider, resulted in unforeseen delays with the project.

Commission regulation and precedent are very clear that service delivery deadlines must be extended under certain circumstances, including delays for reasons beyond the service provider’s control.

Fund Year 2016 E-Rate Administration

Fund Year 2016 was the first year the Administrator utilized the E-Rate Productivity Center (EPC) online portal for virtually all communication between the Administrator and applicants. The Commission has noted in a series of Orders that EPC rollout was plagued with technological issues and has granted relief to a multitude of Fund Year 2016 applicants.

The Commission noted that delays with processing Fund Year 2016 Post-Commitment requests resulted in missed invoice deadlines and granted relief to affected applicants. The Virginia Beach Form 500 was in Administrative review for nine months causing hardship and lost income to both applicant and service provider.

Conclusion

Virginia Beach made every attempt to comply with Commission regulation and Administrator policy with this application. A timely service deadline extension request was submitted to the Administrator detailing the nature of service delivery delays and how those delays were out of the service provider’s control.

Commission regulation is clear that service delivery extensions would apply in this case. Virginia Beach asks the Commission to overturn the Administrator decision and extend the service delivery and invoice deadline for this FRN and allow the service provider to invoice the remaining $145,000 discounted portion of this extensive project.

Alternatively, and in the public interest, Virginia Beach asks the Commission to waive any procedural or minor violations for this FRN. There was absolutely no waste, fraud or program abuse with this or any Virginia Beach E-Rate application.

Respectfully Submitted,

//ss//

Michael Combs

Virginia Beach City Public Schools

P.O. Box 6038

Virginia Beach, VA 23456-0038

757-263-6800

Streamlined Resolution of Requests Related to Actions by the Universal Administrative Company, DA 17-385, rel. April 28, 2017 granting a Service Delivery Extension citing “…extensions of the deadline for service implementation when applicants demonstrated they were unable to complete implementation on time for reasons beyond the service providers’ control…” (footnote 12) CC Docket 02-6. Administrator Website “Before You’re Done” “Service Delivery” Extensions: “The applicant requested an extension because the service provider was unable to complete delivery and installation for reasons beyond the service provider's control.”

Virginia Beach Form 500 Number 71673, General Details section.

January 19, 2018 email from Carolyn McCornac, USAC, to Susan Clair, Virginia state E-Rate coordinator.

Annette Islands School District, DA 12-323, Rel. March 5, 2012 at 1; Streamlined Resolution DA 17-385, Rel. April 28, 2018; 47 C.F.R. § 54.507(d), CC Docket No. 02-6.

Pribilof School District, FCC 18-118, Rel. August 8, 2018 at 3: “Funding year 2016 was the first year E-Rate applicants were required to use the EPC portal.” “…due to unexpected issues with rollout

of EPC, USAC extended the filing window and, for the first time, created a second filing window for a

subset of applicants.”; Jemez Pueblo Tribal Consortium, DA 17-1179, Rel. December 7, 2018 at 4: “USAC’s issuance of funding year 2016 funding commitment decision letters (FCDL) was, however, significantly delayed due to technical and operational challenges.”

DA 18-188, Rel. February 26, 2018, CC Docket 02-6 at 2: “We take this action in response to the extraordinary circumstances created by technological system issues that delayed USAC’s issuance of post-commitment RFCDLs for funding year 2016.”