Before the

FEDERAL COMMUNICATIONS COMMISSION

Washington, D.C. 20554

In the Matter of				)

)

Request for Review of a Decision of the	) Administrator Correspondence Dated

Universal Service Administration Corp. for	) November 17, 2017

King George County Schools, VA		)

)

)

Schools and Libraries Universal Service	)	CC Docket No. 02-6

Support Mechanism				)

Request for Review or Waiver

In accordance with sections 54.719 through 54.721 of the Commission's rules, King George County Schools (King George) requests Federal Communications Commission (Commission) review of a decision of the Schools and Libraries Division of the Universal Service Administrative Company (Administrator).  Consistent with precedent, King George asks the Commission to overturn this decision, waive any procedural deadline and restore badly needed funding for this project.

Form 471 Application Number: 161026283

FRN: 1699130130, 1699129931

Billed Entity Number: 126445

FCC Registration Number: 0014898613

Background

King George Schools, located in central Virginia, serves a relatively rural community between Richmond and Washington, DC.  King George is situated between the Potomac River on the north and Rappahannock River to the south. The major employer is federal, state and local government.

King George applied for E-Rate discounted funding for telecommunications service in 2016 in accordance with newly established regulations for self-provisioned fiber under the Commission’s E-Rate Modernization Order.  After a thorough and protracted review, the project was approved with a Funding Commitment Letter on March 2, 2017.

With approval, King George and its vendor began work. Due to the late funding commitment, the project would not be completed by the original deadline of June 30, 2017. The Commission required all self-provisioned fiber applications to undergo additional scrutiny to ensure cost effectiveness and regulatory compliance resulting in delayed funding. Additionally, the Commission required fiber projects to be completed by June 30 of the relevant fund year, rather than September 30 as is practice for one-time construction projects. Recognizing application review delays would lead to construction delays and inability for applicants to meet the June 30 deadline, the Commission ordered the Administrator to grant construction extensions for applicants that made requests by June 30. On April 21, 2017 the Administrator issued guidance for applicants to apply for extensions. On May 15, 2017 the consultant for King George submitted an extension request in accordance with Administrator instructions. The Administrator, through EPC notification requested the May 15 submission be “certified” in emails on May 15 and 30. The emails were not recognized until July 7, 2017 and were certified immediately.

Between April 2017 and present, the consultant’s father-in-law was undergoing cancer treatment including several hospitalizations and continues to require considerable family assistance caring for him and members of the family. The King George consultant attended to the day-to-day support of his father-in-law and family during the period.

Discussion

King George timely submitted a deadline extension request in accordance with Administrator guidance. The “certification” was a page added to the already submitted spreadsheet that included certifying language. By submitting original information in the deadline extension submission and original spreadsheet, King George was certifying its accuracy in accordance with the Terms of Service for users of the EPC portal. As soon as it was discovered, the certification was submitted on July 7, 2017. Delays were the result of immediate family illness and waiver should be granted in accordance with the Acorn, Academy of Academic Excellence and Greenfield decisions.

It should also be noted that all funding correspondence and Administrator records including the Funding Commitment Letter, Funding Status Tool, and EPC Website indicated and continue to indicate the last date to complete installation for these FRN is September 30, 2017. Submission of the certification was prior to the last date to complete installation as published by the Administrator.

The Commission has recognized that factors such as hardship, equity, and the public interest may properly be taken into consideration when determining whether to grant a waiver for missed deadlines. Particularly in these kinds of cases, where there is a special circumstance and no evidence of any fraud, waste or abuse, the Commission has acknowledged that, “rigid compliance…does not further the purposes of section 254(h) or serve the public interest.”

Conclusion

King George respectfully requests that the FCC waive the filing deadline for the extension certification based on facts presented here. King George also asks the Commission for an expedited decision as a substantial amount of work has been performed and the vendor is in need of payment from the E-Rate fund.

Respectfully submitted November 30, 2017,

Greg Weisiger

Consultant to King George

14504 Bent Creek Ct.

Midlothian, VA 23112

804-302-4406

Acorn Public Library, DA 08-2376, Rel. October 30, 2008; Bishop Perry, FCC 06-54, Rel. May 19,2006; Academy of Academic Excellence, DA 07-1180, Rel. March 9,2007; Greenfield Public School District, DA 06-487, Rel. February 28, 2006 (Deployment)

Modernizing the E-Rate Program for Schools and Libraries, FCC 14-189, rel. December 19, 2014. WC Docket No. 13-184.

Annette Island School District, FCC DA 12-1666, Rel. October 17, 2012 (Annette).  The FCC granted 14 appeals, effectively granting waivers of the Form 486 deadline.

Alaska Gateway Decision, DA 06-1871, Rel. Sept. 14, 2006 (Alaska Gateway), CC Docket No 02-6